## Foglio1
Task Name | Start | Finish | Constraint Date | Predecessors | Work | Resource Names | Duration | Successors | Type | Constraint Type | Early Start | Early Finish | Late Start | Late Finish
Avvio e Planning | Tue 14/10/25 | Fri 19/12/25 | Tue 14/10/25 |  | 192 hrs | Rosa Guida[50%] | 48 days? | 5;6;7;8;9 | Fixed Work | Start No Earlier Than | Tue 14/10/25 | Fri 19/12/25 | Tue 14/10/25 | Mon 22/12/25
PM Gestione | Mon 22/12/25 | Mon 24/08/26 | NA |  | 250 hrs |  | 168,88 days |  | Fixed Duration | As Soon As Possible | Mon 22/12/25 | Mon 24/08/26 | Mon 29/12/25 | Fri 28/08/26
Esecuzione | Mon 22/12/25 | Mon 24/08/26 | Tue 11/08/26 | 7SS;123FF | 175 hrs | Rosa Guida[50%] | 168,88 days |  | Fixed Duration | Finish No Earlier Than | Mon 22/12/25 | Mon 24/08/26 | Mon 29/12/25 | Fri 28/08/26
Monitoraggio e controllo | Mon 22/12/25 | Mon 24/08/26 | Tue 11/08/26 | 7SS;123FF | 75 hrs | Rosa Guida[50%] | 168,88 days |  | Fixed Duration | Finish No Earlier Than | Mon 22/12/25 | Mon 24/08/26 | Mon 29/12/25 | Fri 28/08/26
RAD - Requirements Analysis Document | Mon 22/12/25 | Thu 15/01/26 | NA | 1 | 250 hrs |  | 14,46 days |  | Fixed Duration | As Soon As Possible | Mon 22/12/25 | Thu 15/01/26 | Mon 22/12/25 | Fri 16/01/26
Requirements Elicitation | Mon 22/12/25 | Wed 31/12/25 | NA | 1 | 70 hrs |  | 5,1 days |  | Fixed Duration | As Soon As Possible | Mon 22/12/25 | Wed 31/12/25 | Mon 22/12/25 | Wed 31/12/25
Pacchetto AS-IS | Mon 22/12/25 | Mon 29/12/25 | NA | 1 | 20 hrs | Alessandro Denysenko | 2,5 days | 14;3SS;4SS;13 | Fixed Work | As Soon As Possible | Mon 22/12/25 | Mon 29/12/25 | Tue 23/12/25 | Tue 30/12/25
Mappa stakeholder e obiettivi | Mon 22/12/25 | Tue 23/12/25 | NA | 1 | 8 hrs | Gloria Santangelo | 1 day | 10 | Fixed Work | As Soon As Possible | Mon 22/12/25 | Tue 23/12/25 | Mon 22/12/25 | Tue 23/12/25
Elenco requisiti raccolti | Mon 22/12/25 | Tue 23/12/25 | NA | 1 | 11 hrs | Marianna Afeltra | 1,38 days | 11 | Fixed Work | As Soon As Possible | Mon 22/12/25 | Tue 23/12/25 | Tue 23/12/25 | Mon 29/12/25
Scenari | Tue 23/12/25 | Wed 24/12/25 | NA | 8 | 8 hrs | Gloria Santangelo | 1 day | 12;11 | Fixed Work | As Soon As Possible | Tue 23/12/25 | Wed 24/12/25 | Tue 23/12/25 | Mon 29/12/25
Modello casi d’uso preliminari | Wed 24/12/25 | Mon 29/12/25 | NA | 10;9 | 10 hrs | Marianna Afeltra;Michele Riccio[50%] | 1,02 days | 12;21;20 | Fixed Work | As Soon As Possible | Wed 24/12/25 | Mon 29/12/25 | Mon 29/12/25 | Tue 30/12/25
Pacchetto TO-BE + validazione preliminare | Mon 29/12/25 | Wed 31/12/25 | NA | 10;11 | 13 hrs | Gloria Santangelo;Michele Riccio[50%] | 1,33 days | 15 | Fixed Work | As Soon As Possible | Mon 29/12/25 | Wed 31/12/25 | Tue 30/12/25 | Wed 31/12/25
Requirements Analysis | Mon 29/12/25 | Mon 12/01/26 | NA | 7 | 115 hrs |  | 8,4 days |  | Fixed Duration | As Soon As Possible | Mon 29/12/25 | Mon 12/01/26 | Tue 30/12/25 | Tue 13/01/26
Specifica requisiti funzionali | Mon 29/12/25 | Fri 02/01/26 | NA | 7 | 18 hrs | Alessandro Denysenko | 2,25 days | 16;19 | Fixed Work | As Soon As Possible | Mon 29/12/25 | Fri 02/01/26 | Tue 30/12/25 | Mon 05/01/26
Specifica requisiti non funzionali | Wed 31/12/25 | Fri 02/01/26 | NA | 12 | 18 hrs | Gloria Santangelo;Michele Riccio[50%] | 1,73 days | 16;19 | Fixed Work | As Soon As Possible | Wed 31/12/25 | Fri 02/01/26 | Wed 31/12/25 | Mon 05/01/26
Casi d’uso dettagliati | Mon 05/01/26 | Wed 07/01/26 | NA | 14;15 | 20 hrs | Alessandro Denysenko;Gloria Santangelo | 1,25 days | 17;19 | Fixed Work | As Soon As Possible | Mon 05/01/26 | Wed 07/01/26 | Mon 05/01/26 | Thu 08/01/26
Object Model | Thu 08/01/26 | Fri 09/01/26 | NA | 16;19 | 25 hrs | Alessandro Denysenko;Marianna Afeltra;Gloria Santangelo | 1,04 days | 18 | Fixed Work | As Soon As Possible | Thu 08/01/26 | Fri 09/01/26 | Thu 08/01/26 | Mon 12/01/26
Modello Dinamico | Fri 09/01/26 | Mon 12/01/26 | NA | 17 | 24 hrs | Gloria Santangelo;Michele Riccio[50%];Alessandro Denysenko;Marianna Afeltra | 1,25 days | 22 | Fixed Work | As Soon As Possible | Fri 09/01/26 | Mon 12/01/26 | Mon 12/01/26 | Tue 13/01/26
Matrice di tracciabilità | Wed 07/01/26 | Thu 08/01/26 | NA | 14;15;16 | 10 hrs | Alessandro Denysenko;Gloria Santangelo;Marianna Afeltra;Michele Riccio[50%] | 0,46 days | 17;22 | Fixed Work | As Soon As Possible | Wed 07/01/26 | Thu 08/01/26 | Thu 08/01/26 | Thu 08/01/26
Stesura e Impaginazione RAD | Mon 29/12/25 | Wed 14/01/26 | NA | 11 | 45 hrs |  | 9,69 days |  | Fixed Duration | As Soon As Possible | Mon 29/12/25 | Wed 14/01/26 | Thu 08/01/26 | Wed 14/01/26
Bozza contenuti | Mon 29/12/25 | Mon 05/01/26 | NA | 11 | 20 hrs | Marianna Afeltra | 2,5 days | 22 | Fixed Work | As Soon As Possible | Mon 29/12/25 | Mon 05/01/26 | Thu 08/01/26 | Tue 13/01/26
Documento RAD | Mon 12/01/26 | Wed 14/01/26 | NA | 21;18;19 | 25 hrs | Alessandro Denysenko;Gloria Santangelo;Marianna Afeltra;Michele Riccio[50%] | 1,56 days | 23 | Fixed Work | As Soon As Possible | Mon 12/01/26 | Wed 14/01/26 | Tue 13/01/26 | Wed 14/01/26
Quality Assurance | Wed 14/01/26 | Thu 15/01/26 | NA | 22 | 20 hrs | Alessandro Denysenko;Gloria Santangelo;Marianna Afeltra;Michele Riccio[50%] | 1,25 days | 24 | Fixed Work | As Soon As Possible | Wed 14/01/26 | Thu 15/01/26 | Wed 14/01/26 | Fri 16/01/26
MileStone: RAD Completato | Thu 15/01/26 | Thu 15/01/26 | Thu 15/01/26 | 23 | 0 hrs |  | 0 days | 27;25;26 | Fixed Units | Start No Earlier Than | Thu 15/01/26 | Thu 15/01/26 | Fri 16/01/26 | Fri 16/01/26
SDD - System Design Document | Thu 15/01/26 | Tue 03/02/26 | NA | 24 | 220 hrs |  | 13,41 days |  | Fixed Duration | As Soon As Possible | Thu 15/01/26 | Tue 03/02/26 | Fri 16/01/26 | Wed 04/02/26
Definizione dei Design Goals | Thu 15/01/26 | Wed 21/01/26 | NA | 24 | 21 hrs |  | 3,63 days |  | Fixed Duration | As Soon As Possible | Thu 15/01/26 | Wed 21/01/26 | Fri 16/01/26 | Wed 21/01/26
Catalogo Design Goals e Trade-off | Thu 15/01/26 | Fri 16/01/26 | NA | 24 | 8 hrs | Gloria Santangelo | 1 day | 28;29SS;30SS | Fixed Work | As Soon As Possible | Thu 15/01/26 | Fri 16/01/26 | Fri 16/01/26 | Mon 19/01/26
Matrice di tracciabilità e verbale di validazione obiettivi | Fri 16/01/26 | Wed 21/01/26 | NA | 27 | 13 hrs | Gloria Santangelo | 1,63 days | 49;32 | Fixed Work | As Soon As Possible | Fri 16/01/26 | Wed 21/01/26 | Mon 19/01/26 | Wed 21/01/26
System Decomposition | Thu 15/01/26 | Fri 23/01/26 | NA | 27SS | 37 hrs |  | 5,75 days |  | Fixed Duration | As Soon As Possible | Thu 15/01/26 | Fri 23/01/26 | Fri 16/01/26 | Fri 23/01/26
Elenco dei sottosistemi | Thu 15/01/26 | Mon 19/01/26 | NA | 27SS | 11 hrs | Alessandro Denysenko | 1,38 days | 31SS;34;33 | Fixed Work | As Soon As Possible | Thu 15/01/26 | Mon 19/01/26 | Fri 16/01/26 | Tue 20/01/26
Architettura a livelli | Thu 15/01/26 | Mon 19/01/26 | NA | 30SS | 13 hrs | Marianna Afeltra | 1,63 days | 44SS;32;43SS | Fixed Work | As Soon As Possible | Thu 15/01/26 | Mon 19/01/26 | Fri 16/01/26 | Tue 20/01/26
Specifiche di interfacce e servizi dei sottosistemi | Wed 21/01/26 | Fri 23/01/26 | NA | 28;31 | 13 hrs | Gloria Santangelo | 1,63 days | 49;35;38;40;39 | Fixed Work | As Soon As Possible | Wed 21/01/26 | Fri 23/01/26 | Wed 21/01/26 | Fri 23/01/26
Gestione della Concorrenza | Mon 19/01/26 | Tue 27/01/26 | NA | 30 | 19 hrs |  | 5,75 days |  | Fixed Duration | As Soon As Possible | Mon 19/01/26 | Tue 27/01/26 | Wed 21/01/26 | Tue 27/01/26
Analisi delle criticità di concorrenza | Mon 19/01/26 | Tue 20/01/26 | NA | 30 | 8 hrs | Alessandro Denysenko | 1 day | 35;37;36 | Fixed Work | As Soon As Possible | Mon 19/01/26 | Tue 20/01/26 | Wed 21/01/26 | Thu 22/01/26
Modello di concorrenza | Fri 23/01/26 | Tue 27/01/26 | NA | 34;32 | 11 hrs | Gloria Santangelo | 1,38 days | 49;41 | Fixed Work | As Soon As Possible | Fri 23/01/26 | Tue 27/01/26 | Mon 26/01/26 | Tue 27/01/26
Mappatura Hardware/Software | Tue 20/01/26 | Wed 28/01/26 | NA | 34 | 24 hrs |  | 5,5 days |  | Fixed Duration | As Soon As Possible | Tue 20/01/26 | Wed 28/01/26 | Thu 22/01/26 | Wed 28/01/26
Configurazione dell’ambiente di esecuzione | Tue 20/01/26 | Thu 22/01/26 | NA | 34 | 9 hrs | Alessandro Denysenko | 1,13 days | 38;40;39 | Fixed Work | As Soon As Possible | Tue 20/01/26 | Thu 22/01/26 | Thu 22/01/26 | Fri 23/01/26
Mappatura dei sottosistemi sui nodi e componenti software aggiuntivi | Fri 23/01/26 | Wed 28/01/26 | NA | 37;32;45 | 15 hrs | Marianna Afeltra | 1,88 days | 49;48;47 | Fixed Work | As Soon As Possible | Fri 23/01/26 | Wed 28/01/26 | Mon 26/01/26 | Wed 28/01/26
Gestione dei dati persistenti | Fri 23/01/26 | Wed 28/01/26 | NA | 32;37 | 29 hrs |  | 3,46 days |  | Fixed Duration | As Soon As Possible | Fri 23/01/26 | Wed 28/01/26 | Fri 23/01/26 | Thu 29/01/26
Elenco degli oggetti persistenti e strategia di memorizzazione | Fri 23/01/26 | Tue 27/01/26 | NA | 32;37 | 13 hrs | Alessandro Denysenko | 1,63 days | 41 | Fixed Work | As Soon As Possible | Fri 23/01/26 | Tue 27/01/26 | Fri 23/01/26 | Tue 27/01/26
Architettura di accesso ai dati e schema dati | Tue 27/01/26 | Wed 28/01/26 | NA | 40;35 | 16 hrs | Alessandro Denysenko;Gloria Santangelo;Michele Riccio[50%] | 1,33 days | 42;46 | Fixed Work | As Soon As Possible | Tue 27/01/26 | Wed 28/01/26 | Tue 27/01/26 | Thu 29/01/26
Politiche di Controllo degli Accessi | Fri 30/01/26 | Mon 02/02/26 | NA | 41;46;48 | 16 hrs | Alessandro Denysenko;Gloria Santangelo;Marianna Afeltra;Michele Riccio[50%] | 1 day | 49 | Fixed Work | As Soon As Possible | Fri 30/01/26 | Mon 02/02/26 | Fri 30/01/26 | Mon 02/02/26
Architettura del Control Flow | Thu 15/01/26 | Fri 23/01/26 | NA | 31SS | 24 hrs |  | 6 days |  | Fixed Duration | As Soon As Possible | Thu 15/01/26 | Fri 23/01/26 | Fri 16/01/26 | Mon 26/01/26
Strategia di controllo | Thu 15/01/26 | Tue 20/01/26 | NA | 31SS | 13 hrs | Michele Riccio[50%] | 3,25 days | 45 | Fixed Work | As Soon As Possible | Thu 15/01/26 | Tue 20/01/26 | Fri 16/01/26 | Wed 21/01/26
Elenco degli oggetti di controllo | Tue 20/01/26 | Fri 23/01/26 | NA | 44 | 11 hrs | Michele Riccio[50%] | 2,75 days | 46;38 | Fixed Work | As Soon As Possible | Tue 20/01/26 | Fri 23/01/26 | Wed 21/01/26 | Mon 26/01/26
Boundary Conditions | Wed 28/01/26 | Fri 30/01/26 | NA | 45;41 | 18 hrs | Alessandro Denysenko;Gloria Santangelo;Michele Riccio[50%] | 1,5 days | 49;42 | Fixed Work | As Soon As Possible | Wed 28/01/26 | Fri 30/01/26 | Thu 29/01/26 | Fri 30/01/26
Stesura e Impaginazione SDD | Wed 28/01/26 | Mon 02/02/26 | NA | 38 | 21 hrs |  | 3,63 days |  | Fixed Duration | As Soon As Possible | Wed 28/01/26 | Mon 02/02/26 | Wed 28/01/26 | Tue 03/02/26
Bozza contenuti | Wed 28/01/26 | Fri 30/01/26 | NA | 38 | 13 hrs | Marianna Afeltra | 1,63 days | 49;42 | Fixed Work | As Soon As Possible | Wed 28/01/26 | Fri 30/01/26 | Wed 28/01/26 | Fri 30/01/26
Documento SDD | Mon 02/02/26 | Mon 02/02/26 | NA | 48;28;32;35;38;42;46 | 8 hrs | Alessandro Denysenko;Gloria Santangelo;Marianna Afeltra;Michele Riccio[50%] | 0,5 days | 50 | Fixed Work | As Soon As Possible | Mon 02/02/26 | Mon 02/02/26 | Mon 02/02/26 | Tue 03/02/26
Quality Assurance | Mon 02/02/26 | Tue 03/02/26 | NA | 49 | 11 hrs | Alessandro Denysenko;Gloria Santangelo;Marianna Afeltra;Michele Riccio[50%] | 0,8 days | 51 | Fixed Work | As Soon As Possible | Mon 02/02/26 | Tue 03/02/26 | Tue 03/02/26 | Tue 03/02/26
Milestone: SDD Completato | Tue 03/02/26 | Tue 03/02/26 | Tue 03/02/26 | 50 | 0 hrs |  | 0 days | 52;53;55;54 | Fixed Units | Finish No Earlier Than | Tue 03/02/26 | Tue 03/02/26 | Wed 04/02/26 | Wed 04/02/26
ODD – Object Design Document | Tue 03/02/26 | Thu 19/02/26 | NA | 51 | 190 hrs |  | 11,75 days |  | Fixed Duration | As Soon As Possible | Tue 03/02/26 | Thu 19/02/26 | Wed 04/02/26 | Thu 19/02/26
Trade-offs e specifiche delle interfacce | Tue 03/02/26 | Thu 05/02/26 | NA | 51 | 17 hrs | Marianna Afeltra;Michele Riccio[50%] | 1,79 days | 59 | Fixed Work | As Soon As Possible | Tue 03/02/26 | Thu 05/02/26 | Wed 04/02/26 | Thu 05/02/26
Package Design | Wed 04/02/26 | Thu 12/02/26 | NA | 51 | 42 hrs |  | 6,13 days |  | Fixed Duration | As Soon As Possible | Wed 04/02/26 | Thu 12/02/26 | Wed 04/02/26 | Fri 13/02/26
Catalogo dei package | Wed 04/02/26 | Thu 05/02/26 | NA | 51 | 12 hrs | Alessandro Denysenko | 1,5 days | 56;59 | Fixed Work | As Soon As Possible | Wed 04/02/26 | Thu 05/02/26 | Wed 04/02/26 | Thu 05/02/26
Mappa di responsabilità e dipendenze interne dei package | Fri 06/02/26 | Tue 10/02/26 | NA | 55 | 15 hrs | Alessandro Denysenko | 1,88 days | 57 | Fixed Work | As Soon As Possible | Fri 06/02/26 | Tue 10/02/26 | Mon 09/02/26 | Thu 12/02/26
Documentazione dei design pattern | Tue 10/02/26 | Thu 12/02/26 | NA | 56 | 15 hrs | Alessandro Denysenko;Michele Riccio[50%] | 1,5 days | 64;63 | Fixed Work | As Soon As Possible | Tue 10/02/26 | Thu 12/02/26 | Thu 12/02/26 | Fri 13/02/26
Class Interfaces | Fri 06/02/26 | Thu 12/02/26 | NA |  | 53 hrs |  | 4,5 days |  | Fixed Duration | As Soon As Possible | Fri 06/02/26 | Thu 12/02/26 | Fri 06/02/26 | Thu 12/02/26
Specifiche di responsabilità e interfacce pubbliche delle classi | Fri 06/02/26 | Tue 10/02/26 | NA | 53;55 | 28 hrs | Gloria Santangelo;Marianna Afeltra | 1,75 days | 60;61 | Fixed Work | As Soon As Possible | Fri 06/02/26 | Tue 10/02/26 | Fri 06/02/26 | Tue 10/02/26
Modello degli attributi di classe | Tue 10/02/26 | Thu 12/02/26 | NA | 59 | 11 hrs | Gloria Santangelo | 1,38 days | 62 | Fixed Work | As Soon As Possible | Tue 10/02/26 | Thu 12/02/26 | Tue 10/02/26 | Thu 12/02/26
Modello delle eccezioni e pattern applicati | Tue 10/02/26 | Thu 12/02/26 | NA | 59 | 14 hrs | Marianna Afeltra | 1,75 days | 62 | Fixed Work | As Soon As Possible | Tue 10/02/26 | Thu 12/02/26 | Tue 10/02/26 | Thu 12/02/26
Class Diagram | Thu 12/02/26 | Fri 13/02/26 | NA | 60;61 | 22 hrs | Gloria Santangelo;Marianna Afeltra;Alessandro Denysenko | 0,97 days | 64;63 | Fixed Work | As Soon As Possible | Thu 12/02/26 | Fri 13/02/26 | Thu 12/02/26 | Fri 13/02/26
Stesura e Impaginazione ODD | Fri 13/02/26 | Tue 17/02/26 | NA | 57;62 | 25 hrs |  | 1,96 days |  | Fixed Duration | As Soon As Possible | Fri 13/02/26 | Tue 17/02/26 | Fri 13/02/26 | Tue 17/02/26
Bozza contenuti | Fri 13/02/26 | Mon 16/02/26 | NA | 57;62 | 17 hrs | Alessandro Denysenko;Gloria Santangelo;Marianna Afeltra | 0,71 days | 65 | Fixed Work | As Soon As Possible | Fri 13/02/26 | Mon 16/02/26 | Fri 13/02/26 | Mon 16/02/26
Documento ODD | Mon 16/02/26 | Tue 17/02/26 | NA | 64 | 8 hrs | Michele Riccio[50%];Alessandro Denysenko | 1 day | 66 | Fixed Work | As Soon As Possible | Mon 16/02/26 | Tue 17/02/26 | Mon 16/02/26 | Tue 17/02/26
Quality Assurance | Tue 17/02/26 | Thu 19/02/26 | NA | 65 | 31 hrs | Michele Riccio[50%];Alessandro Denysenko;Gloria Santangelo;Marianna Afeltra | 1,94 days | 67;68 | Fixed Work | As Soon As Possible | Tue 17/02/26 | Thu 19/02/26 | Tue 17/02/26 | Thu 19/02/26
Milestone: ODD Completato | Thu 19/02/26 | Thu 19/02/26 | Thu 19/02/26 | 66 | 0 hrs |  | 0 days | 69 | Fixed Work | Start No Earlier Than | Thu 19/02/26 | Thu 19/02/26 | Thu 19/02/26 | Thu 19/02/26
TP – Test Plan | Thu 19/02/26 | Fri 27/02/26 | NA | 66 | 90 hrs |  | 6,04 days |  | Fixed Duration | As Soon As Possible | Thu 19/02/26 | Fri 27/02/26 | Thu 19/02/26 | Fri 27/02/26
Scope e strategia di test | Thu 19/02/26 | Wed 25/02/26 | NA | 67 | 28 hrs | Alessandro Denysenko;Michele Riccio[50%] | 3,5 days | 71SS;72SS;73;70SS | Fixed Work | As Soon As Possible | Thu 19/02/26 | Wed 25/02/26 | Thu 19/02/26 | Wed 25/02/26
Preparazione dei Test Case | Thu 19/02/26 | Thu 26/02/26 | NA | 69SS | 40 hrs |  | 4,67 days |  | Fixed Duration | As Soon As Possible | Thu 19/02/26 | Thu 26/02/26 | Fri 20/02/26 | Thu 26/02/26
Catalogo Test Items e classificazione | Thu 19/02/26 | Tue 24/02/26 | NA | 69SS | 14 hrs | Gloria Santangelo | 1,75 days | 73 | Fixed Work | As Soon As Possible | Thu 19/02/26 | Tue 24/02/26 | Fri 20/02/26 | Wed 25/02/26
Tecniche di test definite | Thu 19/02/26 | Mon 23/02/26 | NA | 69SS | 12 hrs | Marianna Afeltra | 1,5 days | 73 | Fixed Work | As Soon As Possible | Thu 19/02/26 | Mon 23/02/26 | Mon 23/02/26 | Wed 25/02/26
Suite di test generata e validata internamente | Wed 25/02/26 | Thu 26/02/26 | NA | 71;72;69 | 14 hrs | Gloria Santangelo;Marianna Afeltra;Michele Riccio[50%] | 1,17 days | 74 | Fixed Work | As Soon As Possible | Wed 25/02/26 | Thu 26/02/26 | Wed 25/02/26 | Thu 26/02/26
Stesura e impaginazione del TP | Thu 26/02/26 | Fri 27/02/26 | NA | 73 | 14 hrs | Alessandro Denysenko;Gloria Santangelo;Marianna Afeltra;Michele Riccio[50%] | 0,88 days | 75 | Fixed Work | As Soon As Possible | Thu 26/02/26 | Fri 27/02/26 | Thu 26/02/26 | Fri 27/02/26
Quality Assurance | Fri 27/02/26 | Fri 27/02/26 | NA | 74 | 8 hrs | Alessandro Denysenko;Gloria Santangelo;Marianna Afeltra;Michele Riccio[50%] | 0,5 days | 76 | Fixed Work | As Soon As Possible | Fri 27/02/26 | Fri 27/02/26 | Fri 27/02/26 | Fri 27/02/26
Milestone: TP completato | Fri 27/02/26 | Fri 27/02/26 | Fri 27/02/26 | 75 | 0 hrs |  | 0 days | 79;77;78 | Fixed Work | Start No Earlier Than | Fri 27/02/26 | Fri 27/02/26 | Fri 27/02/26 | Fri 27/02/26
TCS – Test Case Specification | Fri 27/02/26 | Thu 12/03/26 | NA | 76 | 160 hrs |  | 8,88 days |  | Fixed Duration | As Soon As Possible | Fri 27/02/26 | Thu 12/03/26 | Fri 27/02/26 | Thu 12/03/26
Analisi e definizione dei Test Case | Fri 27/02/26 | Mon 09/03/26 | NA | 76 | 110 hrs |  | 5,98 days |  | Fixed Duration | As Soon As Possible | Fri 27/02/26 | Mon 09/03/26 | Fri 27/02/26 | Mon 09/03/26
Identificazione univoca del test | Fri 27/02/26 | Mon 02/03/26 | NA | 76 | 16 hrs | Alessandro Denysenko;Gloria Santangelo;Marianna Afeltra;Michele Riccio[50%] | 1 day | 80 | Fixed Work | As Soon As Possible | Fri 27/02/26 | Mon 02/03/26 | Fri 27/02/26 | Mon 02/03/26
Definizione dell’obiettivo del test | Mon 02/03/26 | Tue 03/03/26 | NA | 79 | 12 hrs | Alessandro Denysenko;Gloria Santangelo;Marianna Afeltra;Michele Riccio[50%] | 0,75 days | 81;82 | Fixed Work | As Soon As Possible | Mon 02/03/26 | Tue 03/03/26 | Mon 02/03/26 | Tue 03/03/26
Definizione input attesi | Tue 03/03/26 | Thu 05/03/26 | NA | 80 | 28 hrs | Gloria Santangelo;Marianna Afeltra | 1,75 days | 83 | Fixed Work | As Soon As Possible | Tue 03/03/26 | Thu 05/03/26 | Tue 03/03/26 | Thu 05/03/26
Definizione output attesi | Tue 03/03/26 | Thu 05/03/26 | NA | 80 | 20 hrs | Alessandro Denysenko;Michele Riccio[50%] | 2,5 days | 83 | Fixed Work | As Soon As Possible | Tue 03/03/26 | Thu 05/03/26 | Tue 03/03/26 | Thu 05/03/26
Procedure speciali necessarie | Thu 05/03/26 | Mon 09/03/26 | NA | 81;82 | 18 hrs | Alessandro Denysenko;Gloria Santangelo;Marianna Afeltra;Michele Riccio[50%] | 1,13 days | 84 | Fixed Work | As Soon As Possible | Thu 05/03/26 | Mon 09/03/26 | Thu 05/03/26 | Mon 09/03/26
Stabilire dipendenze tra test | Mon 09/03/26 | Mon 09/03/26 | NA | 83 | 16 hrs | Alessandro Denysenko;Gloria Santangelo;Marianna Afeltra;Michele Riccio[50%] | 0,61 days | 86;85 | Fixed Work | As Soon As Possible | Mon 09/03/26 | Mon 09/03/26 | Mon 09/03/26 | Mon 09/03/26
Stesura e Impaginazione della Specification | Mon 09/03/26 | Wed 11/03/26 | NA | 84 | 33 hrs |  | 1,84 days |  | Fixed Duration | As Soon As Possible | Mon 09/03/26 | Wed 11/03/26 | Mon 09/03/26 | Wed 11/03/26
Controllo dei test case | Mon 09/03/26 | Tue 10/03/26 | NA | 84 | 12 hrs | Alessandro Denysenko;Gloria Santangelo;Marianna Afeltra;Michele Riccio[50%] | 0,69 days | 87 | Fixed Work | As Soon As Possible | Mon 09/03/26 | Tue 10/03/26 | Mon 09/03/26 | Tue 10/03/26
Inserimento tabelle | Tue 10/03/26 | Tue 10/03/26 | NA | 86 | 8 hrs | Alessandro Denysenko;Gloria Santangelo;Marianna Afeltra | 0,33 days | 88 | Fixed Work | As Soon As Possible | Tue 10/03/26 | Tue 10/03/26 | Tue 10/03/26 | Tue 10/03/26
Impaginazione, numerazione, revisione tecnica interna | Tue 10/03/26 | Wed 11/03/26 | NA | 87 | 13 hrs | Alessandro Denysenko;Gloria Santangelo;Marianna Afeltra;Michele Riccio[50%] | 0,81 days | 89 | Fixed Work | As Soon As Possible | Tue 10/03/26 | Wed 11/03/26 | Tue 10/03/26 | Wed 11/03/26
Quality Assurance | Wed 11/03/26 | Thu 12/03/26 | NA | 88 | 17 hrs | Alessandro Denysenko;Gloria Santangelo;Marianna Afeltra;Michele Riccio[50%] | 1,06 days | 90 | Fixed Work | As Soon As Possible | Wed 11/03/26 | Thu 12/03/26 | Wed 11/03/26 | Thu 12/03/26
Milestone: TCS completato | Thu 12/03/26 | Thu 12/03/26 | Thu 12/03/26 | 89 | 0 hrs |  | 0 days | 91;92 | Fixed Work | Start No Earlier Than | Thu 12/03/26 | Thu 12/03/26 | Thu 12/03/26 | Thu 12/03/26
Sviluppo | Thu 12/03/26 | Tue 16/06/26 | NA | 90 | 1.342 hrs |  | 64,93 days |  | Fixed Duration | As Soon As Possible | Thu 12/03/26 | Tue 16/06/26 | Thu 12/03/26 | Tue 16/06/26
Setup ambiente | Thu 12/03/26 | Wed 18/03/26 | NA | 90 | 70 hrs | Gloria Santangelo;Marianna Afeltra;Michele Riccio[50%];Alessandro Denysenko | 3,25 days | 93 | Fixed Work | As Soon As Possible | Thu 12/03/26 | Wed 18/03/26 | Thu 12/03/26 | Wed 18/03/26
Implementazione e Unit Test | Wed 18/03/26 | Thu 04/06/26 | NA | 92 | 1.131 hrs | Gloria Santangelo;Marianna Afeltra;Michele Riccio[50%];Alessandro Denysenko | 50,39 days | 94 | Fixed Work | As Soon As Possible | Wed 18/03/26 | Thu 04/06/26 | Wed 18/03/26 | Thu 04/06/26
Integrazione e Review | Thu 04/06/26 | Mon 15/06/26 | NA | 93 | 141 hrs | Gloria Santangelo;Marianna Afeltra;Michele Riccio[50%];Alessandro Denysenko | 6,29 days | 98;95 | Fixed Work | As Soon As Possible | Thu 04/06/26 | Mon 15/06/26 | Thu 04/06/26 | Mon 15/06/26
Milestone: Sviluppo terminato | Mon 15/06/26 | Tue 16/06/26 | Mon 15/06/26 | 94 | 0 hrs |  | 0 days | 96;97;101;100;103;104;106 | Fixed Work | Start No Earlier Than | Mon 15/06/26 | Tue 16/06/26 | Mon 15/06/26 | Tue 16/06/26
Testing | Tue 16/06/26 | Wed 05/08/26 | NA | 95 | 560 hrs |  | 36,25 days |  | Fixed Duration | As Soon As Possible | Tue 16/06/26 | Wed 05/08/26 | Tue 16/06/26 | Wed 05/08/26
Test di Integrazione | Tue 16/06/26 | Fri 17/07/26 | NA | 95 | 140 hrs |  | 23,25 days |  | Fixed Duration | As Soon As Possible | Tue 16/06/26 | Fri 17/07/26 | Mon 29/06/26 | Fri 31/07/26
Suite Test di Integrazione | Tue 16/06/26 | Thu 02/07/26 | NA | 94 | 70 hrs | Gloria Santangelo | 8,75 days | 99 | Fixed Work | As Soon As Possible | Tue 16/06/26 | Thu 02/07/26 | Mon 29/06/26 | Wed 15/07/26
Esecuzione e report Test di Integrazione | Thu 02/07/26 | Fri 17/07/26 | NA | 98 | 70 hrs | Gloria Santangelo | 8,75 days | 109 | Fixed Work | As Soon As Possible | Thu 02/07/26 | Fri 17/07/26 | Wed 15/07/26 | Fri 31/07/26
Test Funzionale di Sistema | Tue 16/06/26 | Fri 17/07/26 | NA | 95 | 140 hrs |  | 23,25 days |  | Fixed Duration | As Soon As Possible | Tue 16/06/26 | Fri 17/07/26 | Mon 29/06/26 | Fri 31/07/26
Suite Test Funzionali di Sistema | Tue 16/06/26 | Thu 02/07/26 | NA | 95 | 70 hrs | Marianna Afeltra | 8,75 days | 102 | Fixed Work | As Soon As Possible | Tue 16/06/26 | Thu 02/07/26 | Mon 29/06/26 | Wed 15/07/26
Esecuzione e report Test Funzionali di Sistema | Thu 02/07/26 | Fri 17/07/26 | NA | 101 | 70 hrs | Marianna Afeltra | 8,75 days | 109 | Fixed Work | As Soon As Possible | Thu 02/07/26 | Fri 17/07/26 | Wed 15/07/26 | Fri 31/07/26
Test Non Funzionale del Sistema | Tue 16/06/26 | Mon 13/07/26 | NA | 95 | 112 hrs |  | 18,75 days |  | Fixed Duration | As Soon As Possible | Tue 16/06/26 | Mon 13/07/26 | Tue 16/06/26 | Mon 13/07/26
Piano e set-up test non funzionali | Tue 16/06/26 | Mon 29/06/26 | NA | 95 | 56 hrs | Alessandro Denysenko | 7 days | 105 | Fixed Work | As Soon As Possible | Tue 16/06/26 | Mon 29/06/26 | Tue 16/06/26 | Mon 29/06/26
Esecuzione e report test non funzionali | Mon 29/06/26 | Mon 13/07/26 | NA | 104 | 56 hrs | Alessandro Denysenko | 7 days | 107;109 | Fixed Work | As Soon As Possible | Mon 29/06/26 | Mon 13/07/26 | Mon 29/06/26 | Mon 13/07/26
Test di Usabilità e Qualità | Tue 16/06/26 | Mon 06/07/26 | NA | 95 | 56 hrs | Michele Riccio[50%] | 14 days | 107 | Fixed Work | As Soon As Possible | Tue 16/06/26 | Mon 06/07/26 | Tue 23/06/26 | Mon 13/07/26
Test Alpha | Mon 13/07/26 | Wed 22/07/26 | NA | 106;105 | 28 hrs | Michele Riccio[50%] | 7 days | 108 | Fixed Work | As Soon As Possible | Mon 13/07/26 | Wed 22/07/26 | Mon 13/07/26 | Wed 22/07/26
Test Beta | Wed 22/07/26 | Fri 31/07/26 | NA | 107 | 28 hrs | Michele Riccio[50%] | 7 days | 109 | Fixed Work | As Soon As Possible | Wed 22/07/26 | Fri 31/07/26 | Wed 22/07/26 | Fri 31/07/26
Test di Accettazione | Fri 31/07/26 | Tue 04/08/26 | NA | 99;102;108;105 | 39 hrs | Alessandro Denysenko;Gloria Santangelo;Marianna Afeltra;Michele Riccio[50%] | 2,44 days | 110 | Fixed Work | As Soon As Possible | Fri 31/07/26 | Tue 04/08/26 | Fri 31/07/26 | Tue 04/08/26
Test di Installazione | Tue 04/08/26 | Wed 05/08/26 | NA | 109 | 17 hrs | Alessandro Denysenko;Gloria Santangelo;Marianna Afeltra;Michele Riccio[50%] | 1,06 days | 111 | Fixed Work | As Soon As Possible | Tue 04/08/26 | Wed 05/08/26 | Tue 04/08/26 | Wed 05/08/26
Milestone: Testing terminato | Wed 05/08/26 | Wed 05/08/26 | Wed 05/08/26 | 110 | 0 hrs |  | 0 days | 112;113;114;115;118;119 | Fixed Work | Start No Earlier Than | Wed 05/08/26 | Wed 05/08/26 | Wed 05/08/26 | Wed 05/08/26
Manuale utente e di installazione | Wed 05/08/26 | Fri 21/08/26 | NA | 111 | 190 hrs |  | 11,38 days |  | Fixed Duration | As Soon As Possible | Wed 05/08/26 | Fri 21/08/26 | Wed 05/08/26 | Fri 21/08/26
Preparazione del Manuale Utente | Wed 05/08/26 | Mon 10/08/26 | NA | 111 | 35 hrs |  | 3 days |  | Fixed Duration | As Soon As Possible | Wed 05/08/26 | Mon 10/08/26 | Fri 07/08/26 | Wed 12/08/26
Preparazione del Manuale Utente | Wed 05/08/26 | Fri 07/08/26 | NA | 111 | 9 hrs | Alessandro Denysenko | 1,13 days | 116 | Fixed Work | As Soon As Possible | Wed 05/08/26 | Fri 07/08/26 | Fri 07/08/26 | Tue 11/08/26
Raccolta screenshot e contenuti | Wed 05/08/26 | Fri 07/08/26 | NA | 111 | 10 hrs | Gloria Santangelo | 1,25 days | 116 | Fixed Work | As Soon As Possible | Wed 05/08/26 | Fri 07/08/26 | Fri 07/08/26 | Tue 11/08/26
Definizione struttura del manuale e preparazione contenuti | Fri 07/08/26 | Mon 10/08/26 | NA | 114;115 | 16 hrs | Alessandro Denysenko;Gloria Santangelo | 1 day | 117 | Fixed Work | As Soon As Possible | Fri 07/08/26 | Mon 10/08/26 | Tue 11/08/26 | Wed 12/08/26
Manuale Utente | Mon 10/08/26 | Mon 17/08/26 | NA | 116 | 60 hrs | Alessandro Denysenko;Gloria Santangelo | 3,75 days | 122 | Fixed Work | As Soon As Possible | Mon 10/08/26 | Mon 17/08/26 | Wed 12/08/26 | Wed 19/08/26
Preparazione del Manuale di Installazione | Wed 05/08/26 | Wed 12/08/26 | NA | 111 | 26 hrs |  | 4,5 days |  | Fixed Duration | As Soon As Possible | Wed 05/08/26 | Wed 12/08/26 | Wed 05/08/26 | Wed 12/08/26
Prerequisiti e procedure di installazione definiti | Wed 05/08/26 | Mon 10/08/26 | NA | 111 | 14 hrs | Marianna Afeltra | 1,75 days | 120 | Fixed Work | As Soon As Possible | Wed 05/08/26 | Mon 10/08/26 | Wed 05/08/26 | Mon 10/08/26
Materiale e struttura del Manuale raccolti e definiti | Mon 10/08/26 | Wed 12/08/26 | NA | 119 | 12 hrs | Marianna Afeltra | 1,5 days | 121 | Fixed Work | As Soon As Possible | Mon 10/08/26 | Wed 12/08/26 | Mon 10/08/26 | Wed 12/08/26
Manuale di Installazione | Wed 12/08/26 | Wed 19/08/26 | NA | 120 | 41 hrs | Marianna Afeltra;Michele Riccio[50%] | 5,13 days | 122 | Fixed Work | As Soon As Possible | Wed 12/08/26 | Wed 19/08/26 | Wed 12/08/26 | Wed 19/08/26
Quality Assurance | Wed 19/08/26 | Fri 21/08/26 | NA | 117;121 | 28 hrs | Alessandro Denysenko;Gloria Santangelo;Marianna Afeltra;Michele Riccio[50%] | 1,75 days | 123 | Fixed Work | As Soon As Possible | Wed 19/08/26 | Fri 21/08/26 | Wed 19/08/26 | Fri 21/08/26
Milestone: Manuali terminati | Fri 21/08/26 | Fri 21/08/26 | Fri 21/08/26 | 122 | 0 hrs |  | 0 days | 125;124;3FF;4FF | Fixed Work | Start No Earlier Than | Fri 21/08/26 | Fri 21/08/26 | Fri 21/08/26 | Fri 21/08/26
Chiusura | Fri 21/08/26 | Fri 28/08/26 | NA | 123 | 58 hrs |  | 5,65 days |  | Fixed Duration | As Soon As Possible | Fri 21/08/26 | Fri 28/08/26 | Fri 21/08/26 | Fri 28/08/26
Preparazione dei Deliverable Finali | Fri 21/08/26 | Mon 24/08/26 | NA | 123 | 17 hrs | Alessandro Denysenko;Gloria Santangelo | 1,06 days | 126 | Fixed Work | As Soon As Possible | Fri 21/08/26 | Mon 24/08/26 | Fri 21/08/26 | Mon 24/08/26
Consegna del Prodotto e Documentazione | Mon 24/08/26 | Tue 25/08/26 | NA | 125 | 13 hrs | Marianna Afeltra;Michele Riccio[50%] | 1,33 days | 127 | Fixed Work | As Soon As Possible | Mon 24/08/26 | Tue 25/08/26 | Mon 24/08/26 | Tue 25/08/26
Verifica di Accettazione e Chiusura Tecnica | Tue 25/08/26 | Thu 27/08/26 | NA | 126 | 12 hrs | Alessandro Denysenko;Michele Riccio[50%] | 1,25 days | 128 | Fixed Work | As Soon As Possible | Tue 25/08/26 | Thu 27/08/26 | Tue 25/08/26 | Thu 27/08/26
Archiviazione e Versioning Finale | Thu 27/08/26 | Fri 28/08/26 | NA | 127 | 8 hrs | Gloria Santangelo;Michele Riccio[50%] | 1 day | 129 | Fixed Work | As Soon As Possible | Thu 27/08/26 | Fri 28/08/26 | Thu 27/08/26 | Fri 28/08/26
Retrospective e Lesson Learned | Fri 28/08/26 | Fri 28/08/26 | NA | 128 | 8 hrs | Alessandro Denysenko;Gloria Santangelo;Marianna Afeltra;Michele Riccio[50%] | 0,5 days | 130 | Fixed Work | As Soon As Possible | Fri 28/08/26 | Fri 28/08/26 | Fri 28/08/26 | Fri 28/08/26
Terminazione Progetto | Fri 28/08/26 | Fri 28/08/26 | Fri 28/08/26 | 129 | 0 hrs |  | 0 days |  | Fixed Work | Start No Earlier Than | Fri 28/08/26 | Fri 28/08/26 | Fri 28/08/26 | Fri 28/08/26